Project Plan

Snap Cal

| Industry Partner | Garmin |
| --- | --- |
| Primary Instructor | Laily Ajellu |
| Team Member | Oleg Sanitskii |

Document Revision History

| Revision # | Date |
| --- | --- |
| 1 | Feb-15-2026 |

Table of Contents

Contents

1. Executive Summary	3

2. Project Approvers, Reviews and Distribution List	3

3. Scope	4

4. Deliverables	4

5. Assumptions	4

6. Dependencies	5

7. Risk Management	5

8. Communication	6

9. Task Listing (WBS- Work Breakdown Structure)	7

10. Gantt Chart	7

11. Milestones	8

12. RAM – Responsibility Assignment Matrix	10

13. Approval	10

# 1. Executive Summary

The following describes the project to be executed.

| Objective | Develop a functional Android-based mobile application (SnapCal) as the initial release of a broader health-tracking service ecosystem. The system automates nutrition tracking using Optical Character Recognition (OCR), integrates physical activity data from Garmin / Health Connect, and generates structured weekly progress reports for users. While the current Capstone release focuses on the Android application (MVP), the long-term vision of Snap Cal is to evolve into a cross-platform service that may include web and iOS interfaces built on a scalable architecture. |
| --- | --- |
| Corporate Goals Addressed | - Strengthen expertise in mobile application development and scalable system design (Android, Kotlin, iOS, Swift). - Apply Agile methodologies, sprint-based planning, and structured project documentation practices. - Develop practical experience in API integration, local data persistence, and cross-platform service architecture. - Implement data-driven features including OCR processing and activity analytics to support user-centered health tracking solutions. |
| Planned Start Date | Sept 15, 2025 |
| Planned End Date | Mar 27, 2026 |

# 2. Project Approvers, Reviews and Distribution List

Approvers, reviewers and distribution list

| Project Role | Name | E-mail | Date |
| --- | --- | --- | --- |
| Manager | Oleg Sanitskii | 101466133@georgebrown.ca | Feb-15-2026 |

# 3. Scope

Define the sum total of all of its products and their requirements or features.

| In Scope | Out of Scope |
| --- | --- |
| OCR module for nutrition label recognition | Advanced social sharing features |
| Activity import via Garmin / Health Connect | Monetization (subscriptions / ads) |
| Local database design and storage | Multi-language support |
| Weekly progress report generation | AI-based food recognition from non-label photos |
| Authentication system (basic local user profile) | Enterprise-scale deployment |
| CSV/PDF export functionality | Web platform version (future roadmap item) |
| Manual food entry fallback | iOS version (planned for future expansion beyond current release) |
| Dashboard visualization |  |

# 4. Deliverables

| Deliverable | Description |
| --- | --- |
| OCR Component |  |
| OCR image capture module | Camera or image upload functionality for scanning nutrition labels. |
| OCR text extraction engine | Integration of Optical Character Recognition (OCR) library to extract text from food label images. |
| Nutrition parsing logic | Processing extracted text to identify calories and macronutrients (protein, carbs, fats). |
| Activity Integration |  |
| Garmin / Health Connect API integration | Connection setup and authentication with external activity tracking APIs. |
| Activity data retrieval module | Import of user metrics such as steps, calories burned, and workouts. |
| Activity data mapping | Normalization and storage of retrieved activity data into local database structure. |
| Data Storage |  |
| SQLite database schema | Design of local database tables for food entries, activity data, and reports. |
| Data persistence layer | Implementation of data saving and retrieval logic. |
| Offline data handling | Ensure functionality without constant internet connection. |
| Reporting & Export |  |
| Automatic weekly report generation | Calculation and summarization of calorie intake vs. expenditure. |
| Dashboard visualization | Visual representation of nutrition and activity metrics. |
| CSV/PDF export module | Export functionality for reports in CSV and PDF formats. |
| Documentation & Final Submission |  |
| Git repository | Organized source code with proper documentation and version control. |
| Final presentation | Project demo showcasing functional prototype and system architecture. |
| Project documentation | Updated Project Plan, Status Reports, and meeting minutes. |

# 5. Assumptions

- Team members will contribute approximately 6–8 hours per week throughout the sprint schedule.

- Access to Garmin / Health Connect APIs will remain available for development and testing purposes.

- The OCR library (Tesseract) will provide acceptable recognition accuracy under standard image conditions. OCR accuracy is expected to be ≥ 90%.

- The Android-based MVP will serve as the foundational version of a broader service-oriented architecture.

- The current Capstone release will focus on a single-platform implementation (Android), while future web and iOS versions may reuse the same business logic and data structure design.

- The local SQLite database will be sufficient for MVP functionality without requiring cloud infrastructure.

- No major breaking changes will occur in third-party APIs during the development period.

- Required development tools and SDKs will remain stable and compatible throughout the project timeline.

- Users will grant required permissions for accessing activity and health-related data.

- Future expansion to web and iOS platforms would require additional resources, infrastructure planning, and possible backend redesign beyond the current Capstone scope.

# 6. Dependencies

The successful completion of this project depends on the following internal and external factors:

- Access to Garmin / Health Connect APIs — required for retrieving user activity and calorie data; any access restrictions or policy changes may affect integration functionality.

- Availability and stability of the Tesseract OCR library and trained language models — necessary for accurate extraction of nutrition information from food labels.

- Android Studio development environment and SDK compatibility — required for building, testing, and deploying the Android-based MVP.

- Access to physical Android testing devices or stable emulators — essential for validating OCR, permissions handling, and activity integration features.

- Availability of sample food label images for OCR validation — required for testing recognition accuracy and refining parsing logic.

- Stable third-party API behavior — changes in Garmin or Health Connect API structure, authentication flow, or rate limits may impact system functionality.

- Team collaboration infrastructure (GitHub, version control access, communication tools) — necessary for coordinated development and code integration.

- Instructor milestone approvals and academic timeline alignment — required to ensure project progression meets Capstone evaluation criteria.

- Consistent internet connectivity during development and API testing — necessary for integration validation and report generation involving external data.

- Future cross-platform expansion (web or iOS) would depend on additional infrastructure planning and backend architecture decisions beyond the current Android MVP scope.

# 7. Risk Management

| Potential Risk | Severity (H/M/L) | Likelihood (H/M/L) | Management Strategy |
| --- | --- | --- | --- |
| OCR module produces inaccurate text recognition | Medium | Medium | Use a well-trained OCR model (Tesseract), allow users to manually correct recognized data, and test on diverse sample images. |
| Garmin / Health Connect API limitations or access issues | High | Medium | Implement fallback manual entry for activity data; document API dependencies clearly to adjust quickly if API access changes. |
| Time constraints and workload imbalance | High | High | Prioritize MVP features in early sprints, assign clear ownership per module, and hold weekly check-ins to track progress. |
| Merge conflicts and code integration errors | Medium | Medium | Use Git branching strategy, conduct code reviews, and test merges in a controlled environment before committing to main branch. |
| Scope expansion beyond defined MVP (feature creep) | High | Medium. | Strictly adhere to defined Scope section; evaluate new features only after MVP completion.. |
| Future cross-platform expansion complexity (web/iOS) | Medium | Medium | Keep business logic separated from UI components to support potential future platform extensions.. |
| Loss of local data due to app crash or storage issues | Medium | Low | Implement regular local backups and enable SQLite auto-commit; ensure testing covers unexpected shutdown scenarios. |

# 8. Communication

Reporting

The following reports will be produced;

| Report | Audience | Frequency |
| --- | --- | --- |
| Progress Status Report | Instructor / Team Members | Weekly |
| Revised Project Plan | Instructor. | Per Sprint Update |
| Sprint Review Presentation | Instructor / Class. | End of Sprint |

Meetings

The following meetings/communication will be established;

| Meeting | Purpose | Attendees | Frequency |
| --- | --- | --- | --- |
| Weekly Team Meeting | Discuss progress, blockers, and next tasks | All team members | Weekly. |
| Sprint Review | Present sprint outcomes and gather feedback. | Team + Instructor | End of Sprint |
| Ad-hoc Technical Sync | Solve urgent technical issues (OCR, API, DB) | Oleg, Relevant technical members | As needed |

# 9. Task Listing (WBS- Work Breakdown Structure)

| Reference | Tasks | Duration | Dependency |
| --- | --- | --- | --- |

| A | Design UI mockups and workflow | 1 week | None |
| --- | --- | --- | --- |
| B | Implement OCR food label recognition | 2 weeks | A |
| C | Integrate Garmin / Health Connect API | 2 weeks | A |
| D | Develop local database (SQLite) + storage layer | 1 week | B |
| E | Generate reports and export (PDF/CSV) | 1 week | D |
| F | Testing, documentation, and presentation prep | 1 week | E |

# 10. Gantt Chart

| Task | Week 1 (Sep 8–14) | Week 2 (Sep 15–21) | Week 3 (Sep 22–28) | Week 4 (Sep 29–Oct 5) | Week 5 (Oct 6–12) | Week 6 (Oct 13–19) | Week 7 (Oct 20–26) | Week 8 (Oct 27–Nov 2) | Completed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Kick-off & Analysis | ███ | ███ |  |  |  |  |  |  | ✓ |
| Define Requirements & Personas |  | ███ | ███ |  |  |  |  |  | ✓ |
| Create Project Vision + HLR |  | ███ | ███ |  |  |  |  |  | ✓ |
| Project Plan & Team Charter |  |  | ███ | ███ |  |  |  |  | ✓ |
| Implement OCR Prototype |  |  |  | ███ | ███ | █ |  |  | ☐ |
| Garmin API Integration |  |  |  | ███ | ███ | █ |  |  | ☐ |
| Local DB (Storage & Reports) |  |  |  |  | ███ | ███ |  |  | ☐ |
| Testing & Documentation |  |  |  |  |  | ███ | ███ |  | ☐ |
| Sprint 2 Presentation Prep |  |  |  |  |  |  | ███ | ███ | ☐ |

# 11. Milestones

| Major Activity or Milestone | Estimated Milestone Target date | Owner/Reviewer Team Members |
| --- | --- | --- |
| Project Kick-off & Initial Analysis Completed | Sept 14, 2025 (End of Week 1) | Owner: All Team Members • Reviewer: Anjana Shah |
| Requirements & Personas Approved | Sept 28, 2025 (End of Week 3) | Owner: Oleg Sanitskii • Reviewer: Team |
| Project Vision & High-Level Requirements Finalized | Oct 5, 2025 (End of Week 4) | Owner: Oleg Sanitskii • Reviewer: Anjana Shah |
| Project Plan & Team Charter Submitted | Oct 12, 2025 (End of Week 5) | Owner: Oleg Sanitskii • Reviewer: Anjana Shah |
| OCR Prototype Operational | Oct 19, 2025 (End of Week 6) | Owner: Oleg Sanitskii • Reviewer: Team |
| Garmin API Integration Functional (MVP) | Oct 24, 2025 (Mid Week 7) | Owner: Oleg Sanitskii • Reviewer: Team |
| Local DB and Reporting Modules Completed | Oct 26, 2025 (End of Week 7) | Owner: Omar Romero Garcia • Reviewer: Oleg Sanitskii |
| Testing & Documentation Reviewed | Oct 30, 2025 (Week 8 mid) | Owner: Jacques Vidjanagni • Reviewer: Oleg Sanitskii |
| Sprint 2 Presentation Delivered | Nov 2, 2025 (End of Week 8) | Owner: All Team Members • Reviewer: Anjana Shah |
| Project Plan & Team Charter approved | 2025-10-05 (end of Week 4) | Owner: Oleg Sanitskii • Reviewer: Anjana Shah |
| UI mockups & user flow approved | 2025-10-12 (end of Week 5) | Owner: Jacques Vidjanagni • Reviewer: Team |
| OCR prototype (labels → nutrition parsed) | 2025-10-15 (Week 6) | Owner: Oleg Sanitskii • Reviewer: Team |
| Garmin / Health Connect integration MVP | 2025-10-22 (Week 7) | Owner: Oleg Sanitskii • Reviewer: Team |
| Local DB operational + Weekly report (CSV/PDF) | 2025-10-26 (end of Week 7) | Owner: Omar Romero Garcia • Reviewer: Oleg Sanitskii |
| Sprint 2 demo & submission package ready | 2025-11-02 (end of Week 8) | Owner: All team members • Reviewer: Anjana Shah |

# 12. RAM – Responsibility Assignment Matrix

| Task | Oleg | Omar | Jacques |
| --- | --- | --- | --- |
| OCR Module | P |  | S |
| Garmin / Health Connect Integration | P | S |  |
| Local Database & Reports | S | P |  |
| UI / UX Design |  | S | P |
| Testing / QA | S | P | S |
| Documentation |  | S | P |

Legend:
P = Primary Responsibility
S = Secondary Responsibility

# 13. Approval

The signatures below indicate their approval of the contents of this document.

| Project Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Manager/Developer/ Lead | Oleg Sanitskii | Oleg Sanitskii | Feb-15-2026 |